## Slide 1
Planning for a QAD EE Upgrade
March 21st, 2016
Midwest Users Group

## Slide 2: Goals of this Presentation
Discuss Sample Upgrade Timeline (Phases & Deliverables)
Impact on Financial Organization
Review People, Process, Technology Drivers & Considerations
Provide Review of EE Upgrade Options & Approaches
Review Construct of EE Upgrade Plan

## Slide 3: Bottom Line
Heaviest Functional Resource Impact of an EE Upgrade is on Accounting Organizations.
The EE Financial Software in General Ledger, Accounts Payable, Accounts Receivable and Banking Requires Business Process Design to implement and efficiently use this new Software.
Scope of this Implementation effort will include at a minimum:
  General Ledger and Reporting
  Accounts Payable and Banking (entire module around in/out cash)
  Accounts Receivable and Banking (entire module around in/out cash)

## Slide 4: Sample EE Upgrade - Phases and Deliverables
Phase 4
Development
Future State User Procedures
Completed Data Conversion Methods
Completed Development & Unit Testing
UAT Environment populated
Month 1
Months 3-4
Months 2
Phase 2
Installation and Training
Setup QAD EE 2015 Cloud Environments & Db Administration
Project Kick-off
.Net and Application Training
Project Start
Months 4-5
Phase 1
Scoping and Planning
Confirm Timeline and Cost
Complete Resource Plan
Choose QAD Core Additions
Determine Scope
Approvals - Charter, Resource Allocations, Plan and Budget
Phase 3
Design
Future State Process Flows & Narratives
Data Conversion Checklist
Phase 5
Validation & Testing
User Acceptance Test (UAT) Scripts
Completed and Approved UAT
Remediation & Re-Testing
Phase 6
Launch
End User Training Plan
End User Training
Data Conversion
Detailed Cutover and Support Plan
Live 2015EE Production System and Associated Systems
User Stabilization & Support
First Month End Close Support
Decommission Legacy Systems
Months 5-6
Months 6-7
Business Benefits

## Slide 5: People – Accounting Organization
EE should be considered NEW financial software
All base AP, AR, GL, Fixed Asset, Budgeting, Reporting and Banking functionality has changed
The Accounting Organization will see the heaviest functional impact during the upgrade project
Six Major Areas of Focus during upgrade:
  EE Financial Training
  EE Financial Process Design
  EE Data Conversions / Cleansing
  EE Financial Report Writer Report Development
  EE Financial Procedure Development
  EE Financial User Acceptance Testing
People, Process, Technology

## Slide 6: People - Operations
Unless process design required, operational functional changes are minor
Operations team focus:
  Learning new .Net options / browses
  Data Conversion / Cleansing
  UAT Regression Testing
People, Process, Technology

## Slide 7: Process - Accounting
Again…EE should be considered NEW financial software
To support the use of EE at a company, the components of a new implementation methodology are used:
  EE Financial Training – The Project Team needs to understand the software before it can make design decisions on how the software will be used
  EE Financial Process Design – The Project Team needs to define how the software will be used to support its business, including configuration.
People, Process, Technology

## Slide 8: Process - Accounting
EE Financial Training
  Base Data, GL, AP, AR, FA, Banking, Budgeting
  Use of SAF Codes
    Product Line
    Site
    Item Type
    Item Group
    Region
    Customer Type
    Supplier Type
  Financial Report Writer – often done after design with separate budgeting / reporting sessions
  8 to 12 days
People, Process, Technology

## Slide 9: Process - Accounting
Sample Process Design Agenda – Base Setup Only
People, Process, Technology

## Slide 10: Process - Accounting
Sample Process Design Agenda (cont:)
People, Process, Technology

## Slide 11: Process - Accounting
Sample Process Design Agenda (cont:)
People, Process, Technology

## Slide 12: Process - Accounting
People, Process, Technology
Extra EE Required Data Setup

## Slide 13: Process - Accounting
Base EE Financial Setup to Support Operations - 6 to 8 days
Accounts Payable Process Design - 2 to 3 days
Accounts Receivable Process Design - 2 to 3 days
Fixed Assets Process Design – 2 to 3 days
Banking Process Design – 2 to 3 days
Budgeting & Reporting w/Financial Report Writer – 2 to 3 days
Total Process Design 16 to 23 days
People, Process, Technology

## Slide 14: Key New EE / Financial Functionality
Excel Integration
Bulk Data Load
GL Controls
Deductions
Banking
Financial Report Writer
People, Process, Technology

## Slide 15: Technology – Excel Integration
Provides ease of data loads for EE base data
  Excel integration can be used to upload and update master data
  eg - business relations, and SAF structures. Accounts, Subaccounts, Cost Centers, Projects, SAF’s
  Journal Entries
  With Excel integration, you can:
    Export all records for remote maintenance. You then modify the data and re-import the saved results into QAD EE.
    Create a blank template that consists of column headings for all fields in a business component, and export this template for remote maintenance. You can then create the data in the spreadsheet or load data from another application into the template for importing to the system database.
People, Process, Technology

## Slide 16: Technology – Bulk Data Load
New way to load mass data into EE
Utility allows load of one or more files created from Excel Integration templates
Overcomes limitations of Excel integration which can stop at 300 to 500 records
Can attach multiple files and load in sequence into multiple programs
People, Process, Technology

## Slide 17: Technology – GL Controls
Enhance General Ledger Controls enables constant submodule to general ledger balancing.
  General Ledger Control Accounts for
    AP
    AR
    Inventory
    PO Receipts
  Embedded Journal Entry Approval tools.
  Consistency Checks – verifies the integrity of the financial tables by:
    Comparing GL to Submodule balancing.
    Ensures that mandatory fields in financial tables are populated.
  Transaction level FX Revaluation
People, Process, Technology

## Slide 18: Technology – Deductions
Embedded Accounts Receivable deduction management allows for deduction classification and automated write off limits.
  Define your business specific deduction categories (types)
  Automated write of limits by category
  Automated creation of deduction document on the customer account
People, Process, Technology

## Slide 19: Technology - Banking
The banking module enables inbound and outbound banking transactions supporting EFT, positive pay, automated cash applications and check clearing both at the transaction and general ledger level
Process Incoming Bank File
  Create Customer Payment – payment received
  Pay Customer Payment – check cleared
  Bounce Customer Payment – status -> Bounced – invoice(s) re-opened
  Pay Supplier Payment – status -> Paid
  Bounce Supplier Payment - status -> Bounced – invoice(s) re-opened
  Create Banking Entry – create unallocated bank lines
Use of EDI Ecommerce and Bank Format xml files required
People, Process, Technology

## Slide 20: Technology - FRW
Financial Report Writer CUBE’s support real time financial reporting along with schedule processing and email publishing.
  Cube Daemon Refreshes the cube continuously
  Cubes are defined for all or part of the account transaction string.
  SAFs are reportable in the FRW
  Approximates Consolidation for Multi-Entity Reporting
  Report in alternate chart of accounts
People, Process, Technology

## Slide 21: EE Upgrade Options & Approaches
You Need to Decide on Approach:
Database Conversion - Convert your existing Database (8.6E +) via the QDT audit and conversion programs
Re-Alignment - Create New Database and seed the db with…
  (Cleansed / New ) Master Data
  Open Transactions
  Some Minimal Level of Historical Data (GL)

## Slide 22: Key Approach Considerations
Sample Upgrade Approach Decision Matrix

## Slide 23: Other Upgrade Approach Considerations
Customizations – Financial customizations need re-write
Amount of non-financial (operations) process work
Bar Code Data Collection (Movement to QAS)
On Demand vs. On Premise
BI Solution and Post-Upgrade Reporting

## Slide 24: Construct of an EE Upgrade Plan
External Consulting Effort
Internal Resource Plan
RACI Matrix (Responsible, Accountable, Consulted, Informed)
Project Charter
  Scope
  Timeline
  Budget
  Resources and Organization
  Governance)
Holistic Project Budget

## Slide 25
Thanks! Questions?